## Slide 1
Highlight DLB phase 2: Proposal update and implementation road map
Nasser Yao
Scientist, Molecular Breeder
BecA-ILRI Hub, Nairobi, Kenya
http://hub.africabiosciences.org/
Core team meeting
April 29th -30th , 2019
ILRI, Ethiopia Campus

## Slide 2
DLB phase 2 (DLB2) : The project
ACIAR Program(s) Area | Global Program
Project number | FSC/2013/019v3
Project title | Demand led Plant Variety Design for Emerging Markets in Africa Proposal Variation 2018-2021
Commissioned Organisation | University of Queensland
Proposed start date | 1 April 2019
Proposed finish date | 31 March 2022

## Slide 3
DLB 2: The people and partner institutions
Co-Project Leaders
Title and name | Professor Gabrielle Persley
Position | Professor – University of Queensland School of Agriculture and Food Sciences
Organisation | University of Queensland
Phone | 07 38705504 Mobile +61 416 211 401
Fax | 07 38705504
Email | g.persley@uq.edu.au;
Postal address | School of Agriculture and Food Sciences, University of Queensland, St Lucia, Brisbane 4072
Title and name | Dr Vivienne Anthony
Position | Senior Advisor
Organisation | Syngenta Foundation for Sustainable Agriculture (SFSA)
Phone | Tel +41 613235634 Mobile +41 799093454
Fax | Fax +41 61 3237200
Email | Vivienne.anthony@syngenta.com
Postal address | Syngenta Foundation for Sustainable Agriculture (SFSA) WRO-1002.11.54 P.O. Box 4002 Basel Switzerland

## Slide 4
DLB 2: The people and partner institutions
Co-Chief investigator and administrative contact
Title and name | Professor Kaye Baseford
Position | Professor of Biometry
Organisation | University of Queensland School of Agriculture and Food Sciences
Phone | +61 421 056000
Email | k.e.basford@uq.edu.au
Postal address | School of Agriculture and Food Sciences University of Queensland St Lucia, Brisbane Qld 4072
Title and name | Dr Nathan King
Position | Research Administration Officer
Organisation | University of Queensland
Phone | 07 33657594
Email | n.king@uq.edu.au
Postal address | Office of Sponsored Research Cumbrae Stewart Building No. 72, the University of Queensland St Lucia, Brisbane Qld 4072

## Slide 5
DLB 2: The people and partner institutions
Pan-Africa project coordinator
Title and name | Dr Nasser Yao
Position | Plant breeder, Biosciences eastern and central Africa (BecA)
Organisation | BecA-ILRI Hub, International Livestock Research Institute (ILRI)
Phone | +254 20 4223802
Fax | + 254 20 4223001
Email | n.yao@cgiar.org
Postal address | BecA-ILRI Hub, ILRI, PO Box 30709 Nairobi 00100 Kenya
Street address | BecA-ILRI Hub, ILRI campus, Old Naivasha Rd, Kabete, Nairobi Kenya
Pan Africa Project Coordinator- Biosciences eastern and Central Africa, International Livestock Research Institute (BecA-ILRI Hub) Nairobi Kenya

## Slide 6
DLB 2: The people and partner institutions
African Collaborating Organisation: African Centre for Crop Improvement (ACCI) University of KwaZulu, Natal, South Africa
Collaborating scientist:
Title and name | Professor Shimelis Hussain
Position | Deputy Director
Organisation | African Centre for Crop Improvement (ACCI)
Phone | + 273 326 05524
Fax | + 273 326 05524
Email | Shimelish@ukzn.ac.za
Postal address | ACCI, University of KwaZulu-Natal, P/Bag x01, Scottsville 3209, Pietermaritzburg, South Africa

## Slide 7
DLB 2: The people and partner institutions
African Collaborating Organisation: West Africa Centre for Crop Improvement (WACCI), University of Ghana, Accra, Ghana
Collaborating scientists
Title and name | Professor Eric Y Danquah and Professor Pangirayi Tongoona
Position | Director and Deputy Director
Organisation | West Africa Centre for Crop improvement (WACCI), University of Ghana
Phone | Tel: 233 302 520605
Fax | Fax: 233 302 520604
Email | edanquah@wacci.ug.edu.gh; Ptongoona@wacci.ug.edu.gh
Postal address | WACCI, College of Agriculture and Consumer Sciences, University of Ghana, PMB LG30 Legon Ghana

## Slide 8
DLB 2: The people and partner institutions
African Collaborating Organisation: Pan Africa Bean Research Alliance (PABRA) / International Centre for Tropical Agriculture (CIAT)
Collaborating scientists
Title and name | Drs Jean-Claude Rubyogo, Clare Mukankusi and Roland Chirwa
Position | Senior scientists, Pan Africa Bean Research Alliance (PABRA)
Organisation | PABRA, International Center for Tropical Agriculture (CIAT)
Phone | +255 732 979909
Fax | n/a
Email | j.c.rubyogo@cgiar.org; c.mukankusi@cgiar.org; r.chirwa@cgiar.org
Postal address | PABRA/CIAT, c/o Selian Agricultural Research Institute (SARI) Dodoma Rd P.O. Box 2704 Arusha Tanzania

## Slide 9
DLB 2: The people and partner institutions
African Collaborating Organisation: University of Nairobi
Collaborating Scientist
Title and name | Professor Paul Kimani
Position | Head of Plant Breeding and Biotechnology Program
Organisation | University of Nairobi
Phone | n/a
Fax | n/a
Email | pmkimani@uonbi.ac.ke
Postal address | College of Agriculture and Veterinary Sciences, University of Nairobi, PO Box 29053-00625 Nairobi Kenya

## Slide 10
DLB 2: The Goal and Objectives
Project goal: To contribute to the transformation of African agriculture by enabling small scale farmers to better participate in local and regional markets, by increasing the availability and adoption of high performing varieties that meet market demands.
Objective 1: Best practices in plant variety design:
To enable plant breeders to develop high performing varieties that meet customer requirements and market demand
- Having increased access to and ability to implement start-of-the art knowledge, methodologies and best practices from the public and private sectors on DLPVD.
Objective 2: Education and training
To build capacity within plant breeding programs on Demand Led Variety Design
- Strengthening education and training programs for plant breeders, through post graduate curriculum development and new professional development programs on DLPVD in Africa.
Objective 3: Policy analysis and advocacy:
To provide evidence to support new policy development and investments in PB
- Generate high performing varieties to meet emerging market demands in Africa.

## Slide 11
Objective 1: Best practices in demand led breeding:
To enable plant breeders to develop high performing varieties that meet customer requirements and market demand
No. | Activity | Output | Due date for output | Risks / Assumptions | Applications of outputs
1.1 | Develop PPs &TDs, beans in Ethiopia | At least 2 PPs and 2 TDs for beans, Ethiopia | Dec 1 2019 | Ethiopian breeders adopt best practices in DLB | By Ethiopian national bean breeding program to develop new bean varieties
1.2 | Bean market research in Uganda | Market research study on bean cooking time | Dec 1 2019 | Quality market research team undertakes study | By Ugandan bean breeders to set targets in new varieties with reduced cooking time
1.3 | Develop PPs &TDs, beans in Uganda | At least 2 PPs and 2 TDs for beans, Uganda | Dec 1 2020 | Ugandan breeders adopt best practices in DLB | By Ugandan national bean breeding program to develop new bean varieties
1.4 | Develop PPs &TDs, for tomatoes in Ghana | At least 2 PPs and 2 TDs for tomatoes in Ghana | Dec 1 2020 | Ghanaian breeders adopt best practices in DLB | By Ghanaian national tomato breeding program to develop new bean varieties
1.5 | Develop PPs & TDs on 3 other crops | At least 2 PPs & 2 TDs for each of 3 other crops | Dec 1 2021 | African partners & DLB alumni identify 3 other crops/countries | By (3) national/international crop breeding programs to develop new varieties
Notes: PPs, product profiles; TDs, technical data sheets; DLB, demand led breeding

## Slide 12
Objective 2: Education and training:
To build capacity within national plant breeding programs in Africa
on demand led breeding
No. | Activity | Output | Due date for output | Risks / Assumptions | Applications of outputs
2.1 | Develop new content for new unit on gender & plant breeding | DLB Introductory Unit 8: Gender and Plant Breeding | December 1 2019 | African educators group work with gender specialists to incorporate new content into current DLB introductory course material | By African universities in post graduate curriculum and research institutes for in-service training workshops
2.2 | Develop content for new DLB advanced module on PPs & TDs | DLB Advanced Module 1: “Creating product profiles and technical data sheets” | December 1 2020 | African educators group work with breeders and educators to incorporate advanced module 1 into their education programs | By African universities in post graduate curriculum and research institutes for in-house professional development
2.3 | Develop new module on building the business case for investing in demand led breeding | DLB Advanced Module 2: “Making the case for investing in demand led breeding” | December 1 2021 | African educators group work with economists, breeders & private sector specialist to develop content of new module | By African universities in post graduate curriculum and research institutes for in-house professional development; and by R&D leaders in making the case for national & international investments in breeding programs in Africa

## Slide 13
No. | Activity | Output | Due date for output | Risks / Assumptions | Applications of outputs
2.4 | Identify plant breeders’ professional development needs | Analysis of DLB alumni views on their future professional development | December 1 2019 | Risk of poor response rate from 400 DLB alumni to questionnaire sent by project partners | By DLB project partners in developing new professional development opportunities
2.5 | Develop strategy and communications plan for new “DLB CoP in Africa” | Strategy and communications plan for new “DLB Community of practice in Africa” | December 1 2019 | DLB alumni respond to new opportunities in professional development | By plant breeders and research leaders in African institutions and universities with responsibilities for plant breeding
Objective 2: Education and training
To build capacity within national plant breeding programs in Africa
on demand led breeding

## Slide 14
Objective 3: Policy analysis and advocacy
To provide evidence to support new policy development and investments in plant breeding that will generate high performing varieties to meet emerging market demands in Africa.
No. | Activity | Output | Due date of output | Risks / Assumptions | Applications of outputs
3.1 | Develop methodology & evidence base for creating new business cases in DLB investment | Evidence-base methodology for creating new business cases for increasing investments in plant breeding | December 1 2019 | High quality data is (or is not) available for specific crops or countries, on which to base the business case | By breeders & R&D leaders in developing new business cases for public and private investments in breeding
3.2 | Apply new methodology to develop business case - Beans in Ethiopia | Business case on “Investing in Bean breeding in Ethiopia” | December 1 2020 | High quality data is (or is not) available for beans in Ethiopia, on which to base the business case | By Ethiopian bean breeders & R&D leaders in developing new business cases for public and private investments in breeding new bean varieties for markets
3.3 | Apply new methodology to develop business case - Beans in Uganda | Business case on “Investing in Bean breeding in Uganda” | December 1 2020 | High quality data is (or is not) available for beans in Uganda on which to base the business case | By Ugandan bean breeders & R&D leaders in developing new business cases for public and private investments in breeding new bean varieties for markets

## Slide 15
No. | Activity | Output | Due date of output | Risks / Assumptions | Applications of outputs
3.4 | Apply new methodology to develop business case for Tomatoes in Ghana | Business case on “Investing in Tomato breeding in Ghana” | December 1 2020 | High quality data is (or is not) available for beans in Ghana, on which to base the business case | By Ghanaian breeders & R&D leaders in developing new business cases for public and private investments in breeding new tomato varieties for markets
3.5 | Identify policy issues affecting new crop variety development in Ethiopia | Policy brief on “Demand led breeding in Ethiopia” | December 1 2020 | National commitment to agricultural transformation in Ethiopia | By breeders, policy makers and public and private investors in crop agriculture in Ethiopia
3.6 | Identify policy issues affecting new crop variety development in Ghana | Policy brief on “Demand led breeding in Ghana” | December 1 2020 | National commitment to agricultural transformation in Ethiopia | By breeders, policy makers and public and private investors in crop agriculture in Ethiopia
Objective 3: Policy analysis and advocacy
To provide evidence to support new policy development and investments in plant breeding that will generate high performing varieties to meet emerging market demands in Africa.

## Slide 16
No. | Activity | Output | Due date of output | Risks / Assumptions | Applications of outputs
3.7 | Identify policy issues affecting new crop variety development in southern Africa | Policy brief on “Demand led breeding in southern Africa” | December 1 2021 | National commitment to agricultural transformation in the countries of southern Africa | By breeders, policy makers and public and private investors in crop agriculture in countries of southern Africa
3.8 | Plan and conduct with Crawford Fund a Master Class “Business of Plant Breeding in Africa” | Report on DLB Master class with senior policy makers and R&D leaders in Africa | December 1 2021 | Senior policy makers and R&D leaders willing to participate in Master class in Africa | By senior policy makers and R&D leaders participating in the Master Class
Objective 3: Policy analysis and advocacy
To provide evidence to support new policy development and investments in plant breeding that will generate high performing varieties to meet emerging market demands in Africa.

## Slide 17
  Crosscutting activities, methods and outputs
  Communication
Communication channels will be primarily
- Publications
- Workshops and training activities,
- Developing and disseminating training materials and other information about DLB through the project web site (www.syngentafoundation.org/demand-driven-plant-variety-design)
The DLB website to be developed?
A second volume on “Demand led breeding: from Principles to Practice”
- Will contains the case studies conducted by project partners during 2014 – 17 on implementing DLB approaches within specific crops and countries,
- Will be published by CABI in by December 2019
Additional education materials on DLB

## Slide 18
Additional education materials on demand led breeding
Introduction to Demand led Breeding - Unit 8: Gender and Plant Breeding
Partners:
- Gender related plant breeding program (GREAT) at Cornell University, USA and Makerere University, Uganda
- The CGIAR gender and plant breeding program.
Advanced Module 1: “Creating Product Profiles and Technical Data Sheets”
- with Examples from implementing DLB on beans, tomato and other crop breeding programs in Africa
Advanced Module 2: Making the Case for Investing in Demand led Plant Breeding”
- Including new methodology, types of evidence required,
- with examples, as a basis for developing new business cases to support investments in DLB by public and private sector.
  Crosscutting activities, methods and outputs
  Communication

## Slide 19
Annual Coordination Meeting
- Will involve the project leadership team and African and international partners
- Will be held each year, from 2019-2021.
Questionnaire to communicate with the DLB “Community of practice”
.
- To promote promising new varieties developed by DLPB alumni breeders
Deliverables: “Africa Seeds” catalogue and other promotional material for promising new varieties for each crop, with the accompanying product profile and technical data to verify the attributes of the promising new variety and how/where to access seed of the new variety.
- To identify professional development opportunities for DLB alumni
Aim: To support the continuing professional development of plant breeders and associated crop improvement professionals.
  Crosscutting activities, methods and outputs
  Communication

## Slide 20
Capacity building will be at both the individual and institutional level
Is integral to all three objectives of this project.
Objective 2 focuses solely on capacity building within plant breeding programs in Africa.
The scope of the DLB2’s capacity building activities and outputs cover the following:
- Demand led breeding education materials for inclusion in curriculum and courses for post graduate programs for plant breeders at universities in Africa; and
- New professional development opportunities to support practicing plant breeders and related crop improvement professionals, primarily those working within national plant breeding programs in Africa.
  Crosscutting activities, methods and outputs
  Capacity building

## Slide 21
  Crosscutting activities, methods and outputs
  Monitoring and evaluation
The key indicators of the DLB2 project outcomes to be achieved under each of Objectives 1-3 were described earlier above as the project’s outputs.
Preparation of an annual report each year to described progress on the project
- state on the delivery on the outputs
- progress towards the project outcomes (Section 4.4). The indicators for each of the research outcomes are described in Section 4.4 below, as well as the partners who will be important in the development pathways towards impact.
Progress towards achieving development impacts will also be reported in the Annual Reports for 2019-21.
4.3.4 Intellectual property and other regulatory compliance
All information and data accessed and/or generated through the project will be made publicly available, including through open sourced material available through online access.

## Slide 22
Project outcomes and indicators
Objective 1: Best practices in plant variety design
Outcomes
Increasing use of innovative, market driven approaches to PVD by national, regional and international plant breeding programs in Africa,
Greater availability of new, high performing crop varieties that respond to customer needs and market demand;
Increased levels of adoption by small scale farmers of new crop varieties that meet market needs, for crops grown for food security and/or income generation.
Indicators
New approaches to plant variety design implemented by at least 3 partner breeding programs on target crops in selected countries of Africa
New varieties that fit demand led design criteria released by at least 3 partner breeding programs on target crops in selected countries of Africa
Increased levels of uptake of new varieties of at least 3 target crops by small scale producers in selected countries of Africa
Partners for adoption pathways leading to impact
Beans – PABRA/CIAT; national bean breeding programs in Ethiopia and Ghana
Tomato – WACCI, University of Ghana; Ghana national tomato breeding program; World Vegetable Centre, Benin
Breeding programs in Africa with at least 3 other illustrative crops, e.g. cassava, maize, sorghum.

## Slide 23
Outcomes
Innovative market driven approaches to plant variety design are incorporated within the curricula of national and regional post graduate education programs for plant breeders at universities in Africa.
Plant breeders working within national plant breeding programs in Africa access new professional development programs that incorporate demand driven approaches to plant breeding
Indicators
African universities incorporate teaching modules on demand led plant variety design within their curricula, for at least 3 national and/regional post graduate education programs;
Professional development program for DLB alumni implemented through at least 3 national and/or regional partners in Africa
Partners for adoption pathways leading to impact
ACCI, University of KwaZulu Natal, South Africa
BecA-ILRI Hub, Nairobi, Kenya.
Gender related plant breeding program (GREAT) at Cornell University and Makerere University, Uganda
RUFORUM- Regional network of African agricultural universities
University of Nairobi, Kenya
Makerere University Uganda
WACCI, University of Ghana
Project outcomes and indicators
Objective 2: Education and training

## Slide 24
Project outcomes and indicators
Objective 3: Policy analysis and advocacy
Outcomes
Increased public and private investments in DLB of target crops in selected countries of Africa
Indicators
New investments mobilised for DLB programs for at least 3 crops in 3 countries of Africa
Partners for adoption pathways and impact
Breeding programs in Africa participating in objective 1 on implementing DLB on illustrative crops:
Beans – PABRA/CIAT; national bean breeding programs in Ethiopia and Ghana
Tomato – WACCI, University of Ghana; Ghana national tomato breeding program; World Vegetable Centre, Benin
Breeding programs in Africa with at least 3 other illustrative crops (cassava, maize, sorghum).
African universities and regional education programs on plant breeding
ACCI, University of KwaZulu Natal, South Africa
BecA-ILRI Hub, Nairobi, Kenya.
WACCI, University of Ghana
Public and private investors in new variety development in Africa
AGRA, BMGF, SFSA, World Bank
Bilateral agencies, notably the Governments of Australia, Sweden and USA.
Private seed companies

## Slide 25
Impact Pathways – from project outputs to development impact
Scientific impacts
Better integration of all aspects of market demand into the design of new plant varieties. This includes incorporating demand from :
- Farmers to address biological constraints (drought, pest and diseases and yield)
- Consumers (colour, taste, nutritional value and quality)
- Suppliers along the value chain (storage characteristics, processing and keeping quality).
Increasing use of innovative, market driven approaches, that will lead to:
- Greater availability of new, high performing crop varieties that respond to customer needs and market demand.
- Lead to increasing levels of adoption by farmers in Africa (long term)
- Will contribute to both food security and income generation, at the local and national level for the countries of Africa.

## Slide 26
Next generation breeders undergoing formal post graduate programs in universities
New professional development programs for mid-career breeders working in crop improvement programs in Africa
Built a “community of practice” of some 400 crop improvement professionals in Africa introduced to the principles of demand led breeding through 20 training workshops conducted during 2015-17. These professionals are working on 31 crops within 28 countries of Africa. Approximately 120 of the DLB alumni are African women scientists
Support the CoP through new professional development programs made available through their home institutions,
Provision of tailored assistance to specific breeding programs (promotion in promising new varieties that meet market demands)
Plant breeders in Africa implementing a demand led approach to plant variety design in their long-term breeding programs on specific crops in selected countries.
  Implementation of best practices in DLB closely interlink Education and supported by Policy and advocacy for enabling policies and investments.
Impact Pathways – from project outputs to development impact
Capacity building impacts

## Slide 27
Ex ante economic impact assessment of the value of new varieties
Hypothesis to be tested: The use of more DLPVD by breeders in Africa will lead to increased rates of adoption of high performing varieties (HPV’s) over time.
Approach for ex ante analysis of the likely value of economic benefits due to the increased use of new varieties based on the Centre for International Economics (CIC), Canberra propositions:
Market research, product profiling and other evidence of demand in the design of new plant varieties to be used to determine customer/consumer preferences
Willingness to pay premium price for products that meet customer preferences (high nutrient content; better keeping quality; preferred colour and taste).
Assumptions
- There will be a price premium on HPVs that meet customer/markets preferences; this price will vary for different crops and traits in the market.
- Smallholders would respond to market opportunity of a premium price for HPVs of an individual product and willing to grow HPVs that would be a new income earning opportunity
Estimate to be made in each case on the % of the crop in the country/region that would switch to HPVs (e.g. 10% of total crop to switch to new HPVs)
Impact Pathways – from project outputs to development impact
Community/Economic impacts

## Slide 28
Approach for ex ante analysis of the likely value of economic benefits due to the increased use of new varieties based on the Centre for International Economics (CIC), Canberra propositions
The potential economic value of the adoption of HPV can be estimated using customer willingness to pay for these HPVs.
This willingness to pay is a measure of the consumer welfare gain from the better variety and also the increase in consumer surplus from the variety (In standard evaluation terms)
For example, in developing HPVs for tomatoes in Ghana, an ex ante estimate of the value of new varieties, would be based on estimating (assuming) that consumers would be willing to pay a 5% price premium on better quality tomatoes resulting from new HPV tomato varieties in Ghana (a price premium of k dollars per tonne); and that 10% of the total crop would move to the new HYVs within 5 years of release of the new varieties (y= 10% of the current total value of the crop).
The ex ante estimate of the economic value of the intervention would be: k*y .
Impact Pathways – from project outputs to development impact
Community/Economic impacts

## Slide 29
The policy environment needs to be favourable to enable widespread adoption of customer and market-driven principles and practices into national and international plant breeding programs in Africa.
Building the evidence base to support more market driven policies and investments in plant breeding;
Conduct an awareness and advocacy campaign targeting African policy makers and public and private investors in crop improvement and the seed sector in Africa, including those in the international development community.
At the national level, the project’s policy team will work with senior officials in the Governments of Ethiopia and Ghana to encourage them to mainstream DLB approaches.
Policy makers in both countries will be encouraged to use the project’s findings to mainstream demand led approaches to plant breeding for all crops within their national agricultural research systems (NARS).
The project will support national policy makers in developing an enabling policy environment that is conducive to DLB approaches
The project will provide access to the necessary evidence to build the business cases to support public and private investments in plant breeding on priority crops in target environments.
Impact Pathways – from project outputs to development impact
Policy impacts

## Slide 30
THANK YOU
FOR LISTENING